**Paper 12.1 For Information**

**Demersal Working Group  
19th April 2018**

**NSAC Advice Pipeline   
  
 Updated – 18th April 2018**

|  |  |  |  |
| --- | --- | --- | --- |
| **Advice in Development** | | | |
| **Title** | **Work Commenced / planned** | **Target Completion Date** | **Progress** |
| Implementing the Landing Obligation 2019 – Response to Joint Recommendation (DWG) | 27th March | Sch group request to submit by 26th April | Summary document discussed with Sch Technical Group 11th April  Draft paper to be discussed at DWG meeting 19th April.  LOFG meeting to progress arranged for 20th April |
| Swedish proposal for fisheries conservation measures in the marine protected areas in Kattegat (S&KWG) | 17th April | 19th June  Ex Com | First draft out for comment 17th April to be returned by 24th April |
| TAC Setting (DWG) | 19th April | tbc | Outline paper to be discussed at DWG 19th April |
| **Advice Pipeline** | | | |
| Implementing the Landing Obligation 2019 – Advice for the December Council (DWG) | 20th April | Before end June | Commence work at LOFG meeting 20th April |
| Implementing the Landing Obligation beyond January 2019 (DWG) | 20th April | tbc | To agree workplan at LOFG 20th April |
|  | | | |
| Control Regulation (DWG) | May | 19th June  Ex Com | Establish a Focus Group to draft advice in May once Commission has released proposals |
| NSAC Transition to post Brexit position  (Ex Com) | tbc | tbc | Start work once UK white paper released |
| **Policies in Development** | | | |
| Preparing and Presenting NSAC Advice (Ex Com) | tbc | tbc | Planning meeting in May to update policy |